Compensation and Classification Study Workplan

Dates in bold italic are confirmed; all others are week of.

| STEP | WEEK |
| --- | --- |
| 1: Project Planning and Kick-off Meetings with Executive Director, Project Manager and others (site visit #1) Meet with Management Team Project Review Committee meeting #1 Senior manager interviews (10-12) Letter to employees Establish employee hotline Employee communication meetings and focus groups (4) Compensation Philosophy |        January |
| 2: Classification Plan PDQ Process Draft PDQ Distribute PDQs to all employees (Communications meetings during site visit #1) PDQs returned to Singer Group Singer Group PDQ review |   1/24 1/24 – 1/31 |
| 3: Job Evaluation Whole Job Evaluation Job Evaluation hierarchy Project Review Committee #2 | 1/31 1/31-2/7 2/21 |
| 4: Compensation Plan Define participants and benchmark positions (site visit #1) Draft and approve survey (based on current job descriptions) Pilot Test (MLS) Contact participants (MLS) Send out survey Follow-up phone calls (Singer Group and MLS) Surveys returned to Singer Group Market price | 1/17 1/24 1/24 1/31 1/31 2/14 2/14-2/28 ongoing |
| 5: Develop Pay Structure Market competitiveness and job evaluation analysis Meeting with Project Review Committee (site visit #3) | 4/4 4/4 |
| 6: Salary Ranges and Grade Assignments Develop/revise salary structures and grade structures based on all data assimilated Recommend appropriate changes Draft report, including benefits recommendations | 4/11 4/18 4/25 |
| 7: Implementation Appeals Process – development and administration Final report – (site visit #4) | May TBD |