## METROPOLITAN LIBRARY SYSTEM – COMPENSATION AND CLASSIFICATION

# Project Work Plan – May 9, 2017

Will be updated and shared regularly

| STEP | DATE or (WEEK OF) | NOTES |
| --- | --- | --- |
| 1: Project Planning and Kick-off Pre-planning meetings with Project Managers, Chief Organizational Development Officer & Director of HR (5 calls so far) Develop data and documentation requests; receive information from Metro Prepare for onsite meetings and review data Study Hotline – Metrosingerstudy@singergrp.com Prepare agendas and other materials for on-site meetings and send to Metro Kick-off meeting with Executive Director, Project Managers, Leadership Team (site visit #1) Leadership team and Sr. Library Managers interviews (site visit #1) Compensation Project Committee (CPC) meeting #1 (site visit #1) Employee Communications Meetings + Focus Groups (3) (site visit #1) Branch tours – if time (site visit #1) Letter #1 to all employees Compile and analyze focus group information and send to Metro Web-based all staff survey (compensation/classification & performance) Draft survey; send to Metro Project Managers, PRC & CPC Metro review and approve Launch survey Close survey Compile and analyze survey results Develop communications plan Develop Compensation Philosophy Letter #2 to all employees | May (May 8) | No time Ahead of schedule |
| 2: Classification Review Organization chart, re-org, and current description review Position Description Questionnaire (PDQ) Process for Support Staff Draft PDQ and review by Metro Identify staff to complete PDQs HR distribute to select staff Staff complete PDQ and send to supervisor Supervisors review and send to department head Department heads review and send to HR PDQs returned to Singer Group Singer Group reviews and sends HR list of employees to be interviewed Conduct employee interviews - 8 (via phone) Letter #3 to all employees Position Description Questionnaire (PDQ) Process for Public Services Staff Identify staff to complete PDQs HR distribute to select staff Staff complete PDQ and send to supervisor Supervisors review and send to department head Department heads review and send to HR PDQs returned to Singer Group Singer Group reviews and sends HR list of employees to be interviewed Conduct employee interviews - 12 (via phone) Conduct whole job evaluation | (May 15) May 26 June 2 June 9 June 12 (June 12) (June 19, 26) (June 12) (June 12) June 19 June 30 July 7 July 14 July 17 (July 17) (July 17, 24) Aug |  |
| 3: Custom Salary Survey Define participants and benchmark positions Develop mini-descriptions for benchmark positions Develop additional questions Draft and approve compensation survey Contact participants (Metro) Pilot Test (Metro) Send out survey Follow-up phone calls (Singer Group and Metro) Surveys returned to Singer Group Compensation Project Committee (CPC) meeting #2 (virtual meeting) Augment study finding with published data Compile and analyze Letter #4 to all employees | (May 15) (May 15) (May 15) May 22 (May 22) (May 29) (June 5) (June 5, 12) June June/July (August 7) |  |
| 4: Recommendations and Implementation Design Develop/revise salary structures and grade structures based on all data Present findings and preliminary recommendations to Executive Director, Project Managers and Leadership Team (virtual meeting) Compensation Project Committee (CPC) Meeting #3 (virtual meeting) Revise based on feedback Recommend new or modified compensation and classification plans Design implementation plan Cost analysis (to minimum of pay range) Develop implementation strategy Develop FAQs and other communications as needed Letter #5 to all employees | (Aug 7, 14) (Aug 21) (Aug 21) (Aug 28) (Aug 28) (Sept 4) (Sept 11) (Sept 11) |  |
| 5: Implementation and Final Report Presentations Develop draft report Develop final report Present final report to Executive Director and Commission (onsite meeting #2) Present final report to Project Managers and Leadership Team and Compensation Project Committee (CPC) (onsite meeting #2) Post project employee communications meetings (4) (onsite meeting #2) | (Sept 11) (Sept 18) (Sept 25) (Sept 25) (Sept 25) (Sept 25) |  |
| Ongoing communication with Project Managers | Bi-weekly or as needed |  |